## Slide 1
PV-Copilot
AI-Assisted Signal Detection & Case Triage in Pharmacovigilance
Meridian Biopharma (fictional) | 90-Day Pilot | Prepared by Dana Whitfield

## Slide 2
30-60-90 Day Plan
Day 0-30
Foundation
Sign vendor SOW & data agreement
Stand up sandboxed environment
De-identify 24 months of case data
Calibrate model v0.1
Steering Committee validation sign-off
Day 31-60
Live Pilot
Go-live on real case flow
Weekly concordance measurement begins
Mid-pilot checkpoint review
Tune model to v0.2
Dashboard UAT with PV physicians
Day 61-90
Validate & Decide
Confirm concordance target sustained
Compile validation evidence package
Draft rollout business case
Safety Committee go/no-go
Project retrospective
Meridian Biopharma (fictional)
2

## Slide 3
Pilot Budget
Chart: Total incremental spend: $125,000
| Vendor pilot license | QA / validation support
Budget | 85000 | 40000
Success Criteria
Pilot live with real case flow by Day 60
≥90% AI/human coding concordance sustained 2 consecutive weeks
Zero missed serious/unexpected AE signals
Go/no-go recommendation to Safety Committee by Day 90
Meridian Biopharma (fictional)
3

## Slide 4
KPI Trend — Weeks 5 to 9 of Pilot
Chart: Avg. Case Cycle Time (days) — target ≤1.5
| Baseline | Wk5 | Wk6 | Wk7 | Wk8 | Wk9
Cycle Time (days) | 3.5 | 2.1 | 1.8 | 1.6 | 1.5 | 1.3
Target | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Chart: AI / Human Coding Concordance (%) — target ≥90%
| Wk5 | Wk6 | Wk7 | Wk8 | Wk9
Concordance (%) | 84 | 88 | 90 | 91 | 93
Target | 90 | 90 | 90 | 90 | 90
Meridian Biopharma (fictional)
4

## Slide 5
Top Risks
ID | Risk | Likelihood | Impact | Mitigation
R1 | AI under-codes rare/serious AE terms, missing a signal | Medium | High | 100% human review during pilot; weekly concordance audit by seriousness
R3 | PV physician review capacity insufficient for pilot volume | Medium | Medium | Cap pilot volume at 150 cases/week; escalation path for surge coverage
R4 | Regulatory Affairs raises late objection at Safety Committee | Low | High | Regulatory Affairs seated on Steering Committee from Day 1
Meridian Biopharma (fictional)
5

## Slide 6
Stakeholder Accountability (RACI)
Activity | PM | Sponsor | QA Dir. | PV MDs | Coder SME | Vendor
Vendor SOW & DPA | R | A | C | I | I | C
Model calibration | I | I | I | C | R | A
Validation protocol | C | I | A | C | C | I
Pilot go-live decision | R | A | C | C | C | I
Go/no-go recommendation | R | A | C | C | C | I
R = Responsible A = Accountable C = Consulted I = Informed
Meridian Biopharma (fictional)
6