## Slide 1
RiskLens
AI-Driven Risk Stratification & Care Gap Closure
Alden Health Partners, ACO (fictional) | 90-Day Pilot | Prepared by Priya Nandakumar

## Slide 2
30-60-90 Day Plan
Day 0-30
Setup & Baseline
Sign vendor contract & BAA
Connect claims/pharmacy/CM feeds
Select pilot + control pods
Baseline fairness audit
Steering Committee go/no-go
Day 31-60
Train & Go-Live
Train care managers (both pods)
Go-live: daily risk scores live
Week 1 KPI check vs. control
Care manager feedback session
Mid-pilot fairness re-check
Day 61-90
Validate & Decide
Confirm KPI improvement vs. control
Final fairness/bias audit sign-off
Draft expansion business case
VBC Steering Committee go/no-go
Project retrospective
Alden Health Partners, ACO (fictional)
2

## Slide 3
Pilot Budget
Chart: Total incremental spend: $140,000
| Vendor license + integration | Training & change mgmt | Fairness/bias audit
Budget | 95000 | 20000 | 25000
Success Criteria
Tool live in both pilot pods by Day 45
Time-to-outreach and gap-closure tracked weekly vs. control
No significant scoring disparity across demographic groups
Expansion recommendation to Steering Committee by Day 90
Alden Health Partners, ACO (fictional)
3

## Slide 4
KPI Trend — Weeks 5 to 9 of Pilot
Chart: Time-to-Outreach for High-Risk Patients — target ≤5 days
| Baseline | Wk5 | Wk6 | Wk7 | Wk8 | Wk9
Time-to-outreach (days) | 18 | 12 | 9 | 7.2 | 6.5 | 5.5
Target | 5 | 5 | 5 | 5 | 5 | 5
Chart: Care-Gap Closure Advantage vs. Control (pp) — target +15pp
| Wk5 | Wk6 | Wk7 | Wk8 | Wk9
Gap closure gap (pp vs. control) | 4 | 7 | 10 | 13 | 17
Target | 15 | 15 | 15 | 15 | 15
Alden Health Partners, ACO (fictional)
4

## Slide 5
Top Risks
ID | Risk | Likelihood | Impact | Mitigation
R1 | Model shows scoring disparity across demographic groups | Medium | High | Baseline, mid-pilot, and final independent fairness audits with remediation gate
R2 | Care manager adoption is low; recommendations ignored | Medium | Medium | Champions model, weekly feedback loop, relevance tuning
R4 | Control pod contaminated by informal info-sharing | Low | Medium | Explicit training instruction; control supervisor briefed on isolation
Alden Health Partners, ACO (fictional)
5

## Slide 6
Stakeholder Accountability (RACI)
Activity | PM | Sponsor | Compliance | Analytics | Pod Sup. | Vendor
Vendor contract & BAA | R | A | R | I | I | C
Data feed integration | C | I | I | A | I | R
Baseline fairness audit | C | I | C | C | I | I
Go-live decision | R | A | C | C | C | I
Expansion recommendation | R | A | C | C | C | I
R = Responsible A = Accountable C = Consulted I = Informed
Alden Health Partners, ACO (fictional)
6