## Slide 1
ScribeOS
Ambient Clinical Documentation Copilot Rollout
Crestview Health System (fictional) | 90-Day Pilot | Prepared by Marcus Ilić

## Slide 2
30-60-90 Day Plan
Day 0-30
Security & Design
Sign vendor contract & BAA
Security/privacy risk assessment
Design patient consent workflow
Build & test Epic integration
Steering Committee go/no-go
Day 31-60
Go-Live & Monitor
Staggered go-live, 3 clinics
Weekly documentation-time tracking
First chart-quality audit
Physician feedback session
Consent-compliance spot checks
Day 61-90
Validate & Decide
Confirm doc-time reduction sustained
Final chart-quality & consent audit
Draft system-wide scaling case
Clinical Informatics go/no-go
Project retrospective
Crestview Health System (fictional)
2

## Slide 3
Pilot Budget
Chart: Total incremental spend: $170,000
| Vendor license + Epic integration | Security/privacy assessment | Change mgmt & training
Budget | 120000 | 30000 | 20000
Success Criteria
Live in all 3 pilot clinics by Day 45
≥40% reduction in after-hours documentation time
≥95% of AI-drafted notes need only minor edits
Scaling recommendation to Steering Committee by Day 90
Crestview Health System (fictional)
3

## Slide 4
KPI Trend — Weeks 5 to 9 of Pilot
Chart: After-Hours Documentation Time — target ≤1.3 hrs/day
| Baseline | Wk5 | Wk6 | Wk7 | Wk8 | Wk9
After-hours doc time (hrs/day) | 2.1 | 1.6 | 1.4 | 1.25 | 1.15 | 1.05
Target | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
Chart: Chart Audit Pass Rate (minor-edit-only) — target ≥95%
| Wk7 | Wk8 | Wk9 | Wk10
Note quality pass rate (%) | 97 | 97 | 98 | 98
Target | 95 | 95 | 95 | 95
Crestview Health System (fictional)
4

## Slide 5
Top Risks
ID | Risk | Likelihood | Impact | Mitigation
R1 | Patients decline consent at a higher rate than assumed | Medium | Medium | Track opt-out rate weekly from go-live; non-AI documentation fallback ready
R2 | AI-drafted note contains an error a rushed physician signs | Low | High | Mandatory physician review before signing; chart audits screen specifically for signed errors
R3 | Vendor retains PHI beyond the agreed processing window | Low | High | Contractual retention terms; technical verification in security assessment; periodic log audits
Crestview Health System (fictional)
5

## Slide 6
Stakeholder Accountability (RACI)
Activity | PM | Sponsor | CISO | Compliance | Med. Dir. | Vendor
Vendor contract & BAA | R | A | C | C | I | C
Security risk assessment | C | I | A | C | I | C
Consent workflow design | C | I | I | A | C | I
Go-live decision | R | A | C | C | C | I
Scaling recommendation | R | A | C | C | C | I
R = Responsible A = Accountable C = Consulted I = Informed
Crestview Health System (fictional)
6